## Product Backlog
Product Name:	Robbie Robots					Fields in blue expect your input!
Team ID:	1001179884

Name:	Nicholas Reimherr
Initials:	NRR
Student ID:	1001179884

(Additional names for teams only)
Name:
Initials:
Student ID:

Name:
Initials:
Student ID:

Name:
Initials:
Student ID:

Total Features	Left	Available	Completed	Sprint Ends
Total at Start	32	32
Sprint 1	32	32	1	Mar 28
Sprint 2	31	32	3	Apr 04
Sprint 3	29	32	7	Apr 11
Sprint 4	25	32	9	Apr 18
Sprint 5	23	32	10	Apr 25
Sprint 6	22	32	11	May 02

				Note: Priority of unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
				Sprint # (by team size)					Additional features may be proposed by the student / team but must be approved by the Product Owner in writing
Feature ID	Priority	Status	Actual Sprint #	1	2	3	4	Pts	Cml	As a...	I want to...	So that...	Type	Notes
Create_Parts	1	CO	1	1	1	1	1	21	21	PM	create robot parts	I can define robot models	CLI	No menu required here – run program, create a part
Create_Models	2	CO	2	2	1	1	1	13	34	PM	define new robot models	RRS can sell them to our Beloved Customers	CLI	Menu needed – create parts, then create a robot model
Browse_Models	3	CO	3	2	1	1	1	5	39	BC	browse a catalog of robot models	I can buy one or more robots	CLI	Need to list robots models, then list parts in selected model
Add_Customer	4	CO	3	3	2	1	1	3	42	PB	create a new Beloved Customer	I can keep track of who's buying our products	CLI	The usual name, customer number, phone number, and email address
Add_Salesman	5	CO	3	3	2	1	1	3	45	PB	create a new Sales Associate	I can keep track of my employees' performance	CLI	Name and employee number at a minimum
Create_Orders	6	CO	3	3	2	2	1	8	53	SA	create a robot order for a Customer	I can sell robots and thus do my job well	CLI	Select robot model and quantity, show details with total price
Data_Persistence	7	CO	3	3	2	2	2	13	66	PB	ensure persistence of the RRS data	we don't lose orders or historical data	CLI	(CLI) Write the data to the default filename and reload it next time the program runs
GUI_Menu	8	CO	4	4	3	2	2	3	69	All	open a GUI main window	I can interact with RRS Manager with my mouse	GUI	No menu required here – run program, create a part
GUI_Create_Parts	9	CO	4	4	3	2	2	34	103	PM	create robot parts via GUI dialogs	I can define robot models	GUI	An fl_input centric approach is OK initially, but a custom dialog is worth bonus points (perhaps Create > Robot Part)
GUI_Create_Models	10	CO	5	5	4	3	3	21	124	PM	define new robot models via GUI dialogs	RRS can sell them to our Beloved Customers	GUI	Similar to robot parts (perhaps Create > Robot Model)
GUI_Catalog	11	CO	6	6	4	3	3	8	132	BC	browse a catalog of robots via a GUI report	I can buy one or more robots	GUI	A text output is OK initially, but an attractive HTML-like output is desired (perhaps Report > All Robot Models)
GUI_Orders	12	CO	6		5	4	3	21	153	SA	create a robot order for a Customer via GUI	I can sell robots and thus do my job well	GUI	As with CLI (and you’ll need the CLI to add BC and SA people)
GUI_Manage_order	13	IW	6		5	4	4	13	166	PB	manage a robot order for a Customer via GUI	I can ensure the robot is built and ships	GUI	This will involve a state machine implementation
GUI_Customer	14	CO	6		5	4	4	8	174	PB	create a new Beloved Customer via GUI	I can keep track of who's buying our products	GUI	The usual name, address, phone number, and email address (perhaps Create > Customer)
GUI_Associate	15	CO	6		5	4	4	5	179	PB	create a new Sales Associate via GUI	I can keep track of my employees' performance	GUI	Name and employee number at a minimum (perhaps Create > Sales Associate)
	16	NS			6	5	4	13	192	BC	see pictures of the robots in the GUI catalog	I can see what I'm buying	GUI	Add picture when defining robot model, and show it in the robot model report
	17	NS			6	5	4	5	197	PB	allow the users to save data explicitly via GUI	we can save data without exiting the program	GUI	Write the data to the default filename on command (perhaps File > Save to the default filename)
	18	NS			6	5	4	8	205	PB	allow the users to load data explicitly via GUI	we can manage multiple stores in different files	GUI	Read the data from a user-selected file on command (perhaps File > Open)
	19	NS			6	5	4	8	213	PB	allow the users to save data to a specified name via GUI	we can manage multiple stores in different files	GUI	Write the data to a user-selected file on command and make that fie the default (perhaps File > Save As)
	20	NS				5	5	13	226	PB / SA	view a report of orders per SA in the GUI	I can estimate the value of employees / / I can justify a raise	GUI	A basic text report is fine (perhaps Report > Orders by Sales Associate)
	21	NS				6	5	21	247	All	enable basic login by role and customize the GUI	we don't have options that don't apply to our roles	GUI	User ID might be “sa” for Sales associate with a default password, via a dialog on launch (i.e., in main()),and then make inapplicable menu items inactive – keep it simple
	22	NS				6	5	13	260	All	enable copy and paste from text fields	we can save typing	GUI	Just implement this where the toolkit supports it – not all text widgets do, but it's easy where it's supported
	23	NS				6	6	13	273	BC	view my bill (invoice) in the GUI	I can pay for my robots	GUI	A basic text report is fine initially, but a more attractive HTML report is desired (perhaps Report > Invoice)
	24	NS					6	8	281	BC	view my orders in the GUI	see what I have coming to me	GUI	A basic text report is fine initially, but a more attractive HTML report is desired (perhaps Report > Orders by Customer)
	25	NS					6	8	289	SA	view a sales report in the GUI	I can justify a raise	GUI	A basic text report is fine (perhaps Report > Orders by Sales Associate)
	26	NS					6	8	297	PB	view a report of all orders in the GUI	I can manage the company	GUI	A basic text report is fine (perhaps Report > All Orders)
	27	NS					6	13	310	All	Add multi-level undo	Worry less about making mistakes	GUI	This would be for each Create event (e.g., a new Customer) only (perhaps Edit > Undo)
	28	NS					21	331	BC	see a pie chart of a model's component costs	I can decide if I want a different model	GUI	Consider using Fl_Chart, q.v., (perhaps Report > Robot Model Cost Breakdown)
	29	NS					13	344	SA	create a bulk (2+) order for Customer via GUI	avoid proliferation of orders and paperwork	GUI	Allow more than one robot model (with respective quantity) on a single order
	30	NS					8	352	PM	hide robot parts via GUI	obsolete parts aren't accidentally used	GUI	Mark robot parts as “obsolete” and don't allow adding them to new robot models
	31	NS					8	360	PM	hide robot models via GUI	obsolete robots aren't ordered	GUI	Mark robot models as “obsolete” and don't allow adding them to new orders
	32	NS					21	381	SA	save a draft order and return to it later via GUI	I can multi-task between indecisive customers	GUI	Save an order that hasn't been complete, and allow SA to resume work on it later
Product Backlog Burn Chart
Sprints
Features Remaining at Start of Sprint

## Sprint 01 Backlog
Sprint #	1				*** Example Only – Set up a tab for EACH SPRINT ***
Start on	3 / 21
End on	3 / 28
Demo on	TBD

Total Tasks	20
Day 1 Left	20
Day 2 Left	20
Day 3 Left	18
Day 4 Left	18
Day 5 Left	18
Day 6 Left	10
Day 7 Left	0

Task ID	Feature ID	Category	Type	Assigned To	Description	Status	Notes
1	Create_parts	Architecture	UML	NRR	Create UML Use case diagram	CO
2	Create_parts	Architecture	UML	NRR	Create UML Class Diagram	CO	may be updated as needed
3	Create_parts	Robot_parts	Code	NRR	Created Robot_parts class and protected variables	CO	needs constructor still
4	Create_parts	Robot_parts	Test	NRR	Tested that the Robot_parts class is working as intended	CO
5	Create_parts	Robot_parts	Code	NRR	Create the constructor for creating a Robot part	CO
6	Create_parts	Arm	Code	NRR	Create Arm Class with private variables	CO
7	Create_parts	Arm	Test	NRR	Tested arm class	CO
8	Create_parts	Arm	Code	NRR	Add constructor to Arm class to create an arm part	CO
9	Create_parts	Head	Code	NRR	Create Head class with private variables only	CO
10	Create_parts	Head	Test	NRR	Test Head Class	CO
11	Create_parts	Head	Code	NRR	Add the constructor for creating a Head part	CO
12	Create_parts	Torso	Code	NRR	Create torso class with private variables	CO
13	Create_parts	Torso	Test	NRR	Test Torso class	CO
14	Create_parts	Torso	Code	NRR	Add constructor to Torso class to create a torso part	CO
15	Create_parts	Battery	Code	NRR	Create Battery Class with constructor	CO
16	Create_parts	Battery	Test	NRR	Test battery class	CO
17	Create_parts	Motor	Code	NRR	Create Battery Class with a constructor	CO
18	Create_parts	Motor	Test	NRR	Test Motor Class	CO
19	Create_parts		Code	NRR	Create main method to test adding creating a part	CO	no menu necessary at this point in development process
20	Create_parts		Test	NRR	Test ability to create a new part	CO
Sprint Burn Chart
Tasks
Days

## Sprint 02 Backlog
Sprint #	2				*** Example Only – Set up a tab for EACH SPRINT ***
Start on	3 / 28
End on	4 / 04
Demo on	TBD

Total Tasks	16
Day 1 Left	16
Day 2 Left	16
Day 3 Left	14
Day 4 Left	12
Day 5 Left	12
Day 6 Left	6
Day 7 Left	0

Task ID	Feature ID	Category	Type	Assigned To	Description	Status	Notes
1	Create_models	Architecture	UML	NRR	Check and maintain UML Use case diagram for updates	CO	none necessary during this sprint
2	Create_models	Architecture	UML	NRR	Update UML Class diagram with necessary changes.	CO	may be updated as needed
3	Create_models	Robot_models	Code	NRR	Created Robot_models class with variables and methods	CO	needs constructor still
4	Create_models	View	Test	NRR	Tested that the Robot_models class is working	CO
5	Create_models	View	Code	NRR	Update Menu to include parts, models, browsing and quitting	CO
6	Create_models	View	Test	NRR	Test that the menu is working as intended	CO
7	Create_models	View	Code	NRR	Ported the functionality of creating parts to the menu	CO
8	Create_models	View	Test	NRR	Test ability to create a new part	CO
9	Create_models	Robot_models	Code	NRR	Begin adding ability to create a robot model to the menu	CO
10	Create_models	Robot_models	Test	NRR	Test the ability to create a new model	CO
11	Create_models	Robot_models	Code	NRR	Add vectors to store the models	CO
12	Create_models	Robot_models	Test	NRR	Test vectors	CO
13	Browse_models	Motor	Code	NRR	Add the Browse model option to menu	CO
14	Browse_models	Motor	Test	NRR	Test browse option	CO
15	Browse_models		Code	NRR	Create loop to display all models.	CO
16	Browse_models		Test	NRR	Test browsing feature	CO
Sprint Burn Chart
Tasks
Days

## Sprint 03 Backlog
Sprint #	3				*** Example Only – Set up a tab for EACH SPRINT ***
Start on	4 / 04
End on	4 / 11
Demo on	TBD

Total Tasks	18
Day 1 Left	18
Day 2 Left	18
Day 3 Left	16
Day 4 Left	14
Day 5 Left	14
Day 6 Left	8
Day 7 Left	0

Task ID	Feature ID	Category	Type	Assigned To	Description	Status	Notes
1	-	Architecture	UML	NRR	Check and maintain UML Use case diagram for updates	CO	Added additional methods and fields
2	-	Architecture	UML	NRR	Update UML Class diagram with necessary changes.	CO	may be updated as needed
3	Add_customer	Customer	Code	NRR	Created Customer class and populated fields	CO
4	Add_customer	Customer	Test	NRR	Test implementation of Customer in view	CO
5	Add_salesman	Salesman	Code	NRR	Add Sales_associate class with methods and fields	CO
6	Add_salesman	Salesman	Test	NRR	Test implementation of the Sales_associate class	CO
7	Create_orders	Orders	Code	NRR	Declared the Orders class and methods	CO
8	Create_orders	Orders	Test	NRR	Tested the Orders class	CO
9	Create_orders	Orders	Code	NRR	Defined Orders class and implemented creation into the view.	CO
10	Create_orders	Orders	Test	NRR	Test ability to create an order	CO
11	Data_persistence	Data	Code	NRR	Add save method to each of the 5 parts	CO	data.txt
12	Data_persistence	Data	Test	NRR	Created parts to test save functionality	CO
13	Data_persistence	Data	Code	NRR	Add save method to Customer and Sales_associate classes	CO	data.txt
14	Data_persistence	Data	Test	NRR	Tested ability to save customer and employee data	CO
15	Data_persistence	Data	Code	NRR	Added ability to load the saved parts from the save location	CO	needed ignore() to clear some newlines in the buffer
16	Data_persistence	Data	Test	NRR	Tested the ability to load saved parts	CO
17	Data_persistence	Data	Code	NRR	Added ability to load saved customers and salesman	CO
18	Data_persistence	Data	Test	NRR	Tested ability to load customer and employee data	CO
Sprint Burn Chart
Tasks
Days

## Sprint 04 Backlog
Sprint #	4				*** Example Only – Set up a tab for EACH SPRINT ***
Start on	4 / 11
End on	4 / 18
Demo on	TBD

Total Tasks	14
Day 1 Left	12
Day 2 Left	12
Day 3 Left	12
Day 4 Left	10
Day 5 Left	8
Day 6 Left	6
Day 7 Left	0

Task ID	Feature ID	Category	Type	Assigned To	Description	Status	Notes
1	UML	Architecture	UML	NRR	Check and maintain UML Use case diagram for updates	CO	Added additional methods and fields
2	UML	Architecture	UML	NRR	Update UML Class diagram with necessary changes.	CO	may be updated as needed
3	GUI_Menu	View	Code	NRR	Create a basic window to navigate RRS	CO	basic menu with menu bar currently being used
4	GUI_Menu	View	Test	NRR	Test the menu window	CO
5	GUI_Create_Parts	View	Code	NRR	Add a window to create Head parts	CO	Menu for these can be improved
6	GUI_Create_Parts	View	Test	NRR	Test ability to create Head parts	CO
7	GUI_Create_Parts	View	Code	NRR	Add a window to create Torso parts	CO
8	GUI_Create_Parts	View	Test	NRR	Test ability to create a torso part in gui	CO
9	GUI_Create_Parts	View	Code	NRR	Add a window to create Battery parts	CO
10	GUI_Create_Parts	View	Test	NRR	Test ability to create batteries	CO
11	GUI_Create_Parts	View	Code	NRR	Add a window to create Motor parts	CO
12	GUI_Create_Parts	View	Test	NRR	Test ability to create motor part in GUI	CO
13	GUI_Create_Parts	View	Code	NRR	Add a window to create Arm parts	CO
14	GUI_Create_Parts	View	Code	NRR	Test ability to create an arm part in gui	CO
Sprint Burn Chart
Tasks
Days

## Sprint 05 Backlog
Sprint #	5				*** Example Only – Set up a tab for EACH SPRINT ***
Start on	4 / 18
End on	4 / 25
Demo on	TBD

Total Tasks	10
Day 1 Left	10
Day 2 Left	8
Day 3 Left	7
Day 4 Left	5
Day 5 Left	4
Day 6 Left	2
Day 7 Left	0

Task ID	Feature ID	Category	Type	Assigned To	Description	Status	Notes
1	UML	Architecture	UML	NRR	Check and maintain UML Use case diagram for updates	CO	Added additional methods and fields
2	UML	Architecture	UML	NRR	Update UML Class diagram with necessary changes.	CO	may be updated as needed
3	GUI_Create_Models	View	Code	NRR	Create a menubar entry for defining a model and listing models	CO
4	GUI_Create_Models	View	Test	NRR	Test menu bar entry	CO
5	GUI_Create_Models	View	Code	NRR	Create a window when clicking the menubar button	CO
6	GUI_Create_Models	View	Test	NRR	Test the window	CO
7	GUI_Create_Models	View	Code	NRR	Add fields to the window and callbacks	CO
8	GUI_Create_Models	View	Test	NRR	Test fields	CO
9	GUI_Create_Models	View	Code	NRR	Add the model created by the GUI to the list of models	CO
10	GUI_Create_Models	View	Test	NRR	Test the ability to add a new model	CO
11	GUI_Create_Models	View	Code	NRR	Add ability to list defined models in the menubar	CO
Sprint Burn Chart
Tasks
Days

## Sprint 06 Backlog
Sprint #	6				*** Example Only – Set up a tab for EACH SPRINT ***
Start on	4 / 25
End on	5 / 1
Demo on	TBD

Total Tasks	14
Day 1 Left	14
Day 2 Left	14
Day 3 Left	14
Day 4 Left	10
Day 5 Left	7
Day 6 Left	3
Day 7 Left	0

Task ID	Feature ID	Category	Type	Assigned To	Description	Status	Notes
1	UML	Architecture	UML	NRR	Check and maintain UML Use case diagram for updates	CO	Added additional methods and fields
2	UML	Architecture	UML	NRR	Update UML Class diagram with necessary changes.	CO	may be updated as needed
3	GUI_Browse	View	Code	NRR	Create a menubar entry for browsing a catalog of models	CO
4	GUI_Browse	View	Test	NRR	Test menu bar entry	CO
5	GUI_Browse	View	Code	NRR	Create a window when clicking the browse button	CO
6	GUI_Browse	View	Test	NRR	Test the window	CO
7	GUI_Browse	View	Code	NRR	Extend Data Persistence to models defined by GUI	CO
8	GUI_Browse	View	Test	NRR	Test Persistence	CO
9	GUI_Browse	View	Code	NRR	Load the models when starting up the program	CO
10	GUI_Browse	View	Test	NRR	Test that data is loading properly	CO
11	GUI_Orders	View	Code	NRR	Add a window with fields to create an order in GUI	CO
12	GUI_Orders	View	Test	NRR	Test ability to create orders	CO
13	GUI_Customers	View	Code	NRR	Add window to add new customers to the system	CO
14	GUI_Customers	View	Test	NRR	Test adding customers	CO
15	GUI_Associates	View	Code	NRR	Add ability to add new sales associates to the system	CO
16	GUI_Associates	View	Test	NRR	Test ability to add associates	CO
Sprint Burn Chart
Tasks
Days